## Slide 1: Team Aegle Project Charter & Plan
Team Members:
Joseph Finnegan
Carlos Torres
Karla Hernandez
Joe Martinez
Notes: Carlos - don’t forget to remind people what our project actually is

## Slide 2: Topics
Project Charter
MS Project Plan
Notes: Carlos

## Slide 3: Outreach Storage System Scope
What is the project?
Limitations of the project
Documentation Effort
Implementation Effort
Testing Effort
Guidelines to consider the product “finished”.

## Slide 4: Customer and Audience
Sponsor: Dr. Tiernan
Consumer: Dr. Tiernan and UTA Staff / student organizations
Problem: Managing the Outreach inventory system requires a lot of manual work in order to track all the items available.

## Slide 5: Cost Breakdown
Parts | Cost
Handheld RFID Reader | $600.00
RFID Tags | $20.00
Miscellaneous Items | $30.00
Plastic Crates | $40.00
Server (6 months) | $30.00
Total Cost | $720.00
Notes: Joe

## Slide 6: General Organization
•Project Manager: Karla Hernandez
•Responsibilities:
  Guiding team
  Main point of contact with sponsor and 3rd parties
  Schedules team meetings
  Conflict resolution
Notes: Karla, Carlos & Joe prepare in case Karla doesn’t show up, slides 8 thru 12

## Slide 7: Roles & Responsibilities
•Karla Hernandez
  Team Lead
  Architecture Lead
•Joseph Finnegan
  Software Manager
  Test Lead
  Server Lead
  Risk Manager
Notes: Karla

## Slide 8: Roles & Responsibilities, cont.
•Joe Martinez
  Document Master
  Database Lead
•Carlos Torres
  Project Planner
  Hardware Lead
•Dr. Tiernan
  Project Sponsor
  Provide feedback
Notes: Karla

## Slide 9: Communication Plan
Internal
  Regular team meetings
  Whats App mobile app
  Email
  GitHub
External
  Sponsor Meetings
  Email
Notes: Joe

## Slide 10: Project Oversight
• Team has agreed to have all major deliverables finished one week before due date
• Documents in progress are hosted on GitHub for version control
• Team uses What’s App to communicate informally outside of meetings
Notes: Karla,

## Slide 11: MS Project Plan
Task Breakdown & Estimation
Keeping Track of Progress
Overview of the Project Plan
Updates to the Project Plan
Notes: Carlos

## Slide 12: Task Breakdown & Estimation
Previous SD documents are analyzed
Task are assigned according to team member’s strengths and complexity
Team has a internal deadline of a week before the external deadline
Notes: Complexity based on previous Projects.

## Slide 13: Estimation
Roughly 15 Hours per Week per Person
Around 1920 Hours Total to Complete Project
Estimate Doesn’t Take into Account Other Team Member’s Commitments

## Slide 14: Keeping Track of Progress
The following are use to keep track of progress:
Baseline and Actual Start/Finish
Resource Name
BCWS (Budgeted Cost of Work Scheduled)
ACWP (Actual Cost of Work Performed)
BCWP (Budgeted Cost of Work Performed)
CPI (Cost Performance Index)
SPI (Schedule Performance Index)

## Slide 15: Overview of the Project Plan
Notes: Carlos

## Slide 16: Overview of the Project Plan
Notes: Carlos

## Slide 17: Updates to Plan
Biweekly Meetings
- Tuesdays and Saturdays
- Report progress and update project plan
Updates after any progress
Notes: Carlos

## Slide 18: Project Person-hours Budget
Approximately 6-7 months to complete project
Each person works 15 hours per week
As a 4 man team, this is 1440-1680 hours total over the life of the project
Notes: Joe

## Slide 19: Change Control
Used after detailed design has already begun
Any change must be submitted with a change proposal form
Team must decide if change is important enough to be implemented
Team must revise all design, specification, and planning documents to include change
Notes: Joseph

## Slide 20: Quality Management
Documentation
  Kept on GitHub for version control
  Final versions stored on Google Drive
  Rough drafts reviewed by document master
Software
  Test driven development
  Consumer inclusion
Notes: Joseph

## Slide 21: Quality Management, cont.
Hardware
  Will be evaluated by the entire team
  Each piece of hardware will be assigned a weighted value by team
Testing
  Software will be unit tested as it is being developed
  Hardware will be tested before it is integrated with software
  After individual testing, both software and hardware will be integrated and tested
Notes: Joseph

## Slide 22: Change Management
Roles & Responsibilities
  Project Sponsor
    Will propose/approve any significant changes
    Proposal must be submitted to team with a change request form
    Must meet with team to discuss proposed change
  Project Manager
    Primary point of contact for 3rd parties wishing to contact team
    May use discretion concerning change proposals
Notes: Joseph

## Slide 23: Change Management, cont.
  Project Team
    Discuss and analyze proposed changes
    Estimate additional effort and monetary cost needed
    Team must come to unanimous decision for change
  Mr. O’Dell
    Will be notified of approved changes
    Thoughts will be taken into consideration concerning final change approval
Notes: Joseph

## Slide 24: Change Request Form
Source of Change
Date of Change Request Submission
Description of Change
Justification of Change
Areas for sponsor and team signatures
Notes: Joseph

## Slide 25: Risk Management
Roles & Responsibilities
  Project Sponsor
    Risk Identification from client’s POV
  Project Manager
    Maintain communication with risk manager
    Guiding team and avoiding critical risks
Notes: Karla

## Slide 26: Risk Management, cont.
  Project Team
    Responsible for identifying risks
    Must follow steps stated in risk management plan
  Risk Manager
    Joseph Finnegan is designated Risk Manager
    Will document and keep track of risks that emerge during development
    Monitor risk mitigation process
Notes: Karla

## Slide 27
Risk | Priority | Resolution | Trigger
Choose Correct RFID reader | High | Learn about RFID technology and possibly borrow a testing reader from Dr. Jones | Lack of knowledge related to RFID technology.
Tracking items in the storage room is an unrealistic requirement. | High | Find a technology work around so that we don’t exceed the budget. | Sponsor defines unrealistic requirements.
Lack of RFID technology | High | Dr. Jones Students will train us on RFID technology topics. | Identifying the use of the unknown technology in the requirements phase.
Underestimation of tasks | Medium | Have an internal calendar with early due dates so that we have time in case of a contingency. | Tendency of the team to underestimate hours for the tasks.
Other Work | Low | Distribute the work among the remaining team members. | Team members require to miss a meeting or get assigned extra course work.
Incorrect Project Design | High | Consult with several individuals the correctness of our ADS before turning in the baseline document. | Confusion on how to design the Architecture of the system.
Notes: Karla

## Slide 28: Process To follow
Once a trigger occurs, the team will gather and identify the possible Risk(s) that it will cause
Depending on the severity of the risk the team will either deal with the risk, but mainly avoid it following the resolution plan.
The risk manager will documented all activities / issues and resolutions as well as after mitigation

## Slide 29: Procurement Management
Roles & Responsibility
  Project Sponsor
    Provide suggestions/advice concerning components and services needed
  Project Manager
    Will make final decision on which components and services will be purchased
Notes: Joe

## Slide 30: Procurement Management, cont.
  Project Team
    Will provide project manager with their opinions concerning components/services needed
    Responsible for researching components and services needed
  Mr. O’Dell
    Will make final decision as to which components and services are purchased
Notes: Joe

## Slide 31: Procurement & Timing
Components and services needed will be procured at least 2 weeks in advance
To ensure that all components and services are ready before implementation
Notes: Joe

## Slide 32: Questions?