## Slide 1: Team Aegle Project Charter & Plan
Team Members:
Joseph Finnegan
Carlos Torres
Karla Hernandez
Joe Martinez
Notes: Carlos - don’t forget to remind people what our project actually is

## Slide 2: Topics
MS Project Plan
Project Charter
Notes: Carlos

## Slide 3: MS Project Plan
Task Breakdown & Estimation
Keeping Track of Progress
Overview of the Project Plan
Updates to the Project Plan
Notes: Carlos

## Slide 4: Task Breakdown & Estimation
Previous SD documents are analyzed
Task are assigned according to team member’s strengths and complexity
Team has a internal deadline of a week before the external deadline
Notes: Complexity based on previous Projects.

## Slide 5: Estimation
Roughly 15 Hours per Week per Person
Around 1920 Hours Total to Complete Project
Estimate Doesn’t Take into Account Other Team Member’s Commitments

## Slide 6: Keeping Track of Progress
The following are use to keep track of progress:
Baseline and Actual Start/Finish
Resource Name
BCWS (Budgeted Cost of Work Scheduled)
ACWP (Actual Cost of Work Performed)
BCWP (Budgeted Cost of Work Performed)
CPI (Cost Performance Index)
SPI (Schedule Performance Index)

## Slide 7: Overview of the Project Plan
Notes: Carlos

## Slide 8: Overview of the Project Plan
Notes: Carlos

## Slide 9: Updates to Plan
Biweekly Meetings
- Tuesdays and Saturdays
- Report progress and update project plan
Updates after any progress
Notes: Carlos

## Slide 10: General Organization
•Project Manager: Karla Hernandez
•Responsibilities:
–Guiding team
–Main point of contact with sponsor
–Schedules team meetings
Notes: Karla, Carlos & Joe prepare in case Karla doesn’t show up, slides 8 thru 12

## Slide 11: Project Oversight
•Team has agreed to have all major deliverables finished one week before due date
•Documents in progress are hosted on GitHub for version control
•Team uses group chat app to communicate informally outside of meetings
Notes: Karla,

## Slide 12: Roles & Responsibilities
•Karla Hernandez
–Team Lead
–Architecture Lead
•Joseph Finnegan
–Software Manager
–Test Lead
–Server Lead
–Risk Manager
Notes: Karla

## Slide 13: Roles & Responsibilities, cont.
•Joe Martinez
–Document Master
–Database Lead
•Carlos Torres
–Project Planner
–Hardware Lead
•Dr. Tiernan
–Project Sponsor
–Provide feedback
Notes: Karla

## Slide 14: Project Constraints
•Limited Time
–Project must be delivered in roughly 6 months
•Limited Budget
–Budget of $800
–Could constrain hardware design
•Lack of Knowledge
–Team has no experience with RFID technology
Notes: Karla

## Slide 15: Project Person-hours Budget
Approximately 6-7 months to complete project
Each person works 15 hours per week
As a 4 man team, this is 1440-1680 hours total over the life of the project
Notes: Joe

## Slide 16: Cost Breakdown
Parts | Cost
Handheld RFID Reader | $600.00
RFID Tags | $20.00
Miscellaneous Items | $30.00
Plastic Crates | $40.00
Server (6 months) | $30.00
Total Cost | $720.00
Notes: Joe

## Slide 17: Scope Management
Will meet with our sponsor every week
Discuss project status and address concerns
Notes: Joseph

## Slide 18: Change Control
Used after detailed design has already begun
Any change must be submitted with a change proposal form
Team must decide if change is important enough to be implemented
Team must revise all design, specification, and planning documents to include change
Notes: Joseph

## Slide 19: Quality Management
Documentation
  Kept on GitHub for version control
  Final versions stored on Google Drive
  Rough drafts reviewed by document master
Software
  Test driven development
  Consumer inclusion
Notes: Joseph

## Slide 20: Quality Management, cont.
Hardware
  Will be evaluated by the entire team
  Each piece of hardware will be assigned a weighted value by team
Testing
  Software will be unit tested as it is being developed
  Hardware will be tested before it is integrated with software
  After individual testing, both software and hardware will be integrated and tested
Notes: Joseph

## Slide 21: Communication Plan
Internal
  Regular team meetings
  Whats App mobile app
  Email
  GitHub
External
  Sponsor Meetings
  Email project document to sponsor
  Project Supervisor
Notes: Joe

## Slide 22: Change Management
Roles & Responsibilities
  Project Sponsor
    Will propose/approve any significant changes
    Proposal must be submitted to team with a change request form
    Must meet with team to discuss proposed change
  Project Manager
    Primary point of contact for 3rd parties wishing to contact team
    May use discretion concerning change proposals
Notes: Joseph

## Slide 23: Change Management, cont.
  Project Team
    Discuss and analyze proposed changes
    Estimate additional effort and monetary cost needed
    Team must come to unanimous decision for change
  Mr. O’Dell
    Will be notified of approved changes
    Thoughts will be taken into consideration concerning final change approval
Notes: Joseph

## Slide 24: Change Request Form
Source of Change
Date of Change Request Submission
Description of Change
Justification of Change
Areas for sponsor and team signatures
Notes: Joseph

## Slide 25: Risk Management
Roles & Responsibilities
  Project Sponsor
    Risk Identification from client’s POV
  Project Manager
    Maintain communication with risk manager
    Guiding team and avoiding critical risks
Notes: Karla, Joseph prepares for slides 23 to 27 in case Karla doesn’t show up

## Slide 26: Risk Management, cont.
  Project Team
    Responsible for identifying risks
    Must follow steps stated in risk management plan
  Risk Manager
    Joseph Finnegan is designated Risk Manager
    Will document and keep track of risks that emerge during development
    Monitor risk mitigation process
Notes: Karla

## Slide 27: Risks Identified
Category | Risk | Probability | Cost
Technology | Choose correct RFID reader | 20% | 14
Sponsor | Tracking items in the storage room is an unrealistic requirement. | 100% | 15
Team | Lack of RFID Technology knowledge | 100% | 23
Team | Underestimation of tasks | 35% | 2
Team | Other work | 75% | 2
Team | Incorrect Project Design | 15% | 18
Total | 74 |  | 
Notes: Karla

## Slide 28: Risk Severity
Choose correct RFID reader: High
Tracking item location: High
Task underestimation: Medium
Incorrect project design: High
Notes: Karla

## Slide 29: Risk Documentation
Risks will be documented by risk manager
Risk manager will create mitigation plan
All risks mitigated will continue to be monitored
Notes: Karla

## Slide 30: Procurement Management
Roles & Responsibility
  Project Sponsor
    Provide suggestions/advice concerning components and services needed
  Project Manager
    Will make final decision on which components and services will be purchased
Notes: Joe

## Slide 31: Procurement Management, cont.
  Project Team
    Will provide project manager with their opinions concerning components/services needed
    Responsible for researching components and services needed
  Mr. O’Dell
    Will make final decision as to which components and services are purchased
Notes: Joe

## Slide 32: Procurement & Timing
Components and services needed will be procured at least 2 weeks in advance
To ensure that all components and services are ready before implementation
Notes: Joe

## Slide 33: Description of Items/Services
RFID Reader
RFID tags
Antennas
Cables to connect Antenna to reader
Ethernet cable
Host computer